## DIAGNOSIS
Area of the company | You learned about the most common internal factors of a crisis within a company. However, these are general statements that require clarification and a specific diagnosis, which you should conduct in order to develop a Turnaround plan. Based on the answers provided in the exercises, as well as your knowledge, experience, and familiarity, divide your company into the following areas: strategy, employees, finances, quality, technology, and others. In each area, select the processes you will analyze. What works well and what needs improvement? What is the cause of the difficulties? Remember the importance of self-awareness and not confusing causes with symptoms. | not working | working poorly | Working adequately | Working well | Working very well | Working excellently
|  | 0 | 1 | 2 | 3 | 4 | 5
STRATEGY
|  | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 0 | 0 | 0 | 0 | 0
FINANCE
|  | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 0 | 0 | 0 | 0 | 0
PEOPLE
|  | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 0 | 0 | 0 | 0 | 0
QUALITY
|  | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 0 | 0 | 0 | 0 | 0
TECHNOLOGY
|  | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 0 | 0 | 0 | 0 | 0
OTHERS
|  | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 0 | 0 | 0 | 0 | 0
|  | 1 | 0 | 0 | 0 | 0 | 0

## GOALS AND ACTIONS
Plan of Priority Goals and Actions - Template - TURNAROUND PLAN
OWNER/ TURNAROUND TEAM:........................................................................................................................................................................................................................................................................................................................................................................ | [16 empty] | DATE::…...........................................................................
How to use the template: Modify the Turnaround plan template according to your needs. Each Turnaround transformation will be different. Define the phase of the Turnaround. For each objective, specify which general area it pertains to. Is it a strategic, operational, or financial area? The objective itself may be too general and interpreted differently. The guide explains how important it is to "practicalize" objectives through their decomposition and operationalization. Use the action rows to specify in more detail what needs to be done in this area and what results you expect. Assign a responsible person. In the date columns, use the gray field to specify the agreed deadline for achieving the objectives/actions. Use a checkmark to indicate real progress as of the review date. Where are you really in terms of achieving this objective? Determine the status of the objective/action and add comments if necessary | [16 empty] | NEXT MEETING:….............................................................................................................
IMPLEMENTATION
[10 empty] | x | = Progress at Review
[5 empty] | 2023 | [11 empty] | Status | REMARKS/ DETAILS
TURNAROUND PHASE | TURNAROUND | GOAL | SPECIFIC ACTIONS | RESPONSIBLE | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Resilience Phase | Financial | [15 empty] | In progress, According to plan | bar: 2023 Jun
Alarm Phase | Strategic | [15 empty] | Not Started, Not According to Plan (Fill out Corrective Action Sheet) | bar: 2023 Oct
Alarm Phase | Operational | [15 empty] | In Progress, Not According to Plan (Fill out Corrective Action Sheet) | bar: 2023 Aug
Alarm Phase | Operational
Alarm Phase | Operational
Alarm Phase | Strategic
Stabilization Phase | Financial | bar: 2023 Jun
Stabilization Phase | Financial
Stabilization Phase | Strategic | bar: 2023 Jul
Stabilization Phase | Strategic | bar: 2023 Jul
Alarm Phase | Operational | bar: 2023 Jul
Stabilization Phase | Financial
Alarm Phase | Strategic
Alarm Phase | Financial
Alarm Phase | Operational
Alarm Phase | Operational
Alarm Phase | Strategic
Alarm Phase | Operational
Resilience Phase | Financial
Stabilization Phase | Strategic
Stabilization Phase | Operational
Stabilization Phase | Strategic
Alarm Phase | Financial
Stabilization Phase | Strategic
Alarm Phase | Operational
Resilience Phase | Financial
Statusy:
In progress, According to plan
In Progress, Not According to Plan (Fill out Corrective Action Sheet)
Not Started, According to Plan
Not Started, Not According to Plan (Fill out Corrective Action Sheet)
Financial
Strategic
Operational
Alarm Phase
Stabilization Phase
Resilience Phase

## INDICATORS SHEET
Turnaround Objectives/Actions (as specified in the previous sheet) | It is very important to define the results of the Turnaround plan objectives/actions in a measurable way. Use the indicators sheet to precisely specify the expected values for each month. Monitor the achievement of these assumptions during Turnaround plan reviews. For objectives that are harder to quantify, try to find a solution that will allow you to monitor their progress in one place—the Turnaround indicators sheet.
| RESPONSIBLE | <YYYY> YTD ACT |  | JAN. | FEB. | MAR. | APR. | MAY | JUN. | JUL. | AUG. | SEPT. | OCT. | NOV. | DEC.
|  | 1200 | ASSUMPTION | 200 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
EXECUTION
ASSUMPTION
EXECUTION
ASSUMPTION
EXECUTION
ASSUMPTION
EXECUTION
ASSUMPTION
EXECUTION
ASSUMPTION
EXECUTION
ASSUMPTION
EXECUTION
ASSUMPTION
EXECUTION
ASSUMPTION
EXECUTION
ASSUMPTION
EXECUTION

## CORRECTIVE ACTION SHEET
CORRECTIVE ACTION SHEET |  | Respond to any deviations from the plan. Diagnose the causes of deviations and irregularities in the implementation of the Turnaround plan.
Name of Turnaround goal/action | Problem/ Causes | Corrective actions | Responsible | Status | Remarks/Details
(D) Action Completed 50%
(D) Action Completed 50%
(C) Action Completed 100%
|  |  |  | (A) Problem solved |  | (P) Planned Action
|  |  |  | (P) Planned Action |  | (D) Action Completed 50%
|  |  |  | (P) Planned Action |  | (C) Action Completed 100%
|  |  |  | (D) Action Completed 50% |  | (A) Problem solved
(D) Action Completed 50%
(A) Problem solved